## Slide 1
ROADMAP TO DELIVERY
Creating executive alignment on product direction, discovery maturity and delivery certainty
CEO • CTO • Head of Product • Head of Sales
Core idea: one source of truth, different questions, progressively higher certainty.
September 2026
01
Notes: Today I want to separate three things that have become mixed together: product direction, discovery readiness, and delivery certainty. The objective is not to defend a Product artifact. It is to create a shared operating contract so the CEO, CTO and Sales can all get the information they need from one source of truth.

## Slide 2
EXECUTIVE DIAGNOSIS
The real problem is not the roadmap — it is certainty
Product Roadmap • Discovery • Delivery
CEO
“Where are we investing — and when will customers actually get it?”
CTO
“Do not imply an Engineering commitment before the solution is mature and feasible.”
Head of Sales
“What can I tell a customer, and how certain is the date?”
Today, one quarterly JPD view is being asked to answer all three questions.
Before fixing the operating model, we should acknowledge why that lack of certainty is uncomfortable.
02
Notes: The recurring disagreement is really about certainty. The CEO needs portfolio visibility and credible timing. Sales needs to know what can be said to customers. The CTO needs to protect Engineering from dates that have not been validated. Product needs to communicate future direction before every bet is fully discovered. Those needs are all legitimate. Before we discuss the operating model, I want to acknowledge the human and business impact of not having enough visibility.

## Slide 3
LEADERSHIP EMPATHY
Uncertainty is a legitimate leadership concern
Product Roadmap • Discovery • Delivery
CEO
Carries portfolio, revenue and credibility risk. Needs a dependable view of what is likely, when, and with what confidence.
CTO
Carries feasibility, capacity and delivery risk. Needs protection from premature scope and date commitments.
Head of Sales
Carries customer, deal and renewal risk. Needs clear guidance on what can be communicated — and how confidently.
When future delivery is hard to see, discomfort is rational — not a failure to understand Product.
Our job is to replace hidden uncertainty with visible maturity, honest confidence and progressively narrower delivery forecasts.
03
Notes: Before we debate definitions, I want to acknowledge the concern behind the debate. If you are accountable for revenue, customer commitments, engineering capacity or company credibility, not seeing a dependable delivery outlook is uncomfortable. That is a legitimate leadership need. Product should not answer it by asking everyone to tolerate ambiguity. We should answer it with better visibility: what is directional, what is mature, what has a forecast, what is committed, and how confidence increases over time. The goal is not false certainty; it is managed uncertainty.

## Slide 4
OPERATING MODEL
Three questions require three connected management layers
Product Roadmap • Discovery • Delivery
1. PRODUCT ROADMAP
Where should we invest, and roughly when?
Goals • Themes • Bets • Priority • Target quarter
2. DISCOVERY / READINESS
How much do we know — and are we ready?
Evidence • PRD • Prototype • Validation • Artefact Ready
3. DELIVERY / RELEASE PLAN
When can customers realistically get it?
Scope • Dependencies • Capacity • Milestones • Forecast
Connected ≠ collapsed
A single source of truth can expose all three layers without pretending they are the same decision.
04
Notes: The response to that legitimate need is not to force one artifact to pretend it can provide certainty it does not yet have. Research across Atlassian, Productboard, Aha!, ProductPlan, airfocus and Pendo consistently separates strategic roadmapping from detailed delivery planning. I propose three connected layers: roadmap for investment direction and sequencing; discovery/readiness for uncertainty reduction; and delivery/release planning for credible customer availability. Connected does not mean collapsed.

## Slide 5
CURRENT STATE
Our JPD passes the research-based roadmap test
Product Roadmap • Discovery • Delivery
Goals
STRATEGY / WHY
Themes
PRIORITY / WHERE
Solutions / bets
DIRECTION / WHAT
Quarter
SEQUENCING / WHEN
Discovery maturity
STATUS / CONFIDENCE
Artefact Ready
READINESS SIGNAL
Published definitions converge on strategy, priorities, direction, sequencing/time and progress — not “every item has a finished PRD/prototype.”
Our remaining gap is a delivery-certainty contract: what does a quarter promise, and when does an item become committed?
05
Notes: Rather than arguing from opinion, apply a roadmap test. Does the artifact connect to strategy? Does it show priorities and product direction? Does it provide sequencing or a time horizon? Does it show progress or confidence? Our JPD does: goals, themes, solutions, quarters, discovery maturity and Artefact Ready. Published definitions do not require every future item to have a finished PRD and prototype before it can appear. The unresolved issue is what level of delivery certainty each item carries.

## Slide 6
CTO ALIGNMENT
The CTO is right about delivery integrity — not about making completed discovery the definition of a roadmap
Product Roadmap • Discovery • Delivery
The CTO is right about…
• Immature work cannot carry a high-confidence delivery promise.
• PRD/prototype/technical validation can materially change scope.
• Engineering dependencies and capacity affect the date.
• A roadmap quarter must not silently become an Engineering commitment.
But requiring Artefact Ready before roadmap visibility would…
• Hide future strategic direction until late.
• Force detailed discovery too early.
• Turn the roadmap into a near-term delivery pipeline.
• Make discovery a prerequisite to deciding what deserves discovery investment.
Resolution: protect delivery integrity with a Definition of Committed — not by redefining the roadmap as “only fully discovered work.”
06
Notes: I want to explicitly acknowledge the CTO's valid concern. Immature work cannot responsibly carry a high-confidence delivery promise. Feasibility, dependencies, scope and capacity matter. Where I would draw the line differently is using completed discovery as the definition of a roadmap. That would hide future direction and turn the roadmap into a near-term delivery pipeline. The better protection is an explicit Definition of Committed.

## Slide 7
ROADMAP CONTRACT
The critical semantic decision: what does “Q2” mean?
Product Roadmap • Discovery • Delivery
Recommended definition
Q2 = current planning intent / target horizon based on what we know today. Selected items may become commitments — but the quarter label alone is not the commitment.
If Q2 means roadmap intent
Early discovery items can be visible. Confidence varies. The roadmap remains strategic and forward-looking.
If Q2 means guaranteed availability
Only capacity-backed, sufficiently mature items can appear. That artifact is effectively a delivery/release plan.
Choose the semantics explicitly — do not let each function infer its own meaning.
07
Notes: We need one semantic decision. A quarter on the roadmap should mean our current target horizon based on what we know today. It can contain committed items, but the quarter itself is not what creates the commitment. Commitment comes from an explicit status backed by readiness, feasibility, dependencies and capacity. If we instead decide every quarterly label is a guaranteed customer date, then only delivery-ready work can appear and we should call that artifact a release plan.

## Slide 8
DISCOVERY MODEL
Our maturity model mirrors JPD’s own separation of discovery, readiness and delivery
Product Roadmap • Discovery • Delivery
Hypothesis
Strategic rationale
Problem validated
Evidence of need
Solution validation
Prototype / tests
Artefact Ready
Required product artifacts complete
Committed
Capacity + dependencies agreed
Artefact Ready
Product definition is sufficiently mature for robust delivery planning.
Committed
Product + Engineering have agreed scope, feasibility, dependencies and capacity to the required threshold.
08
Atlassian JPD workflow: Discovery → Ready for delivery → Delivery.
Notes: This is especially important because our existing Discovery Maturity and Artefact Ready model is not a weakness; it is the mechanism for progressively reducing uncertainty. Atlassian's own JPD guidance separates Discovery, Ready for delivery and Delivery. So Artefact Ready should be the readiness threshold for robust delivery planning, not the admission ticket to the roadmap. Committed comes after Product and Engineering have agreed the required delivery conditions.

## Slide 9
DELIVERY CERTAINTY
Progressive certainty: narrow the delivery window as uncertainty falls
Product Roadmap • Discovery • Delivery
Roadmap
Q3
LOW
Validated
Aug–Sep
LOW–MED
Artefact Ready
Aug 15–Sep 15
MEDIUM
In delivery
Aug 28–Sep 8
HIGH
Committed
Sep 3
VERY HIGH
The business gets more certainty — not false precision.
Every delivery date should carry a confidence level or status. Precision increases as discovery, feasibility and execution reduce uncertainty.
09
Notes: CEO and Sales are right to ask for better dates. The answer is progressive certainty, not false precision. Early bets may only have a target quarter. As discovery and engineering planning progress, the forecast narrows from a quarter to a month or range and eventually to a committed release window. Every forecast should carry a confidence signal so nobody converts low-confidence roadmap intent into a customer promise.

## Slide 10
CEO VIEW
One portfolio view can show strategy and delivery certainty together
Product Roadmap • Discovery • Delivery
Initiative
Why
Roadmap
Maturity
Delivery forecast
Confidence
Data automation
Retention
Q4
Artefact Ready
Nov 15–30
High
Reporting redesign
Enterprise growth
Q4
Artefact Ready
December
High
Benchmarking
Expansion
Q1
Solution validation
Jan–Feb
Medium
AI recommendations
Differentiation
Q2
Problem validated
Q2
Low
Agentic workflows
New workflows
Q3
Hypothesis
—
Very low
The CEO can now separate “why are we investing?” from “how certain is the date?”
10
Notes: The CEO should not have to choose between strategy and delivery visibility. This portfolio view combines both: why we are investing, the roadmap horizon, maturity, delivery forecast and confidence. That allows two different questions: is this still the right bet, and how credible is the current delivery forecast?

## Slide 11
SALES VIEW
Sales needs a communication contract, not unrestricted access to roadmap dates
Product Roadmap • Discovery • Delivery
VISION
Discuss direction
No delivery promise
PLANNED
Discuss planned value
Timing is indicative
FORECAST
Use approved range
Still explicitly a forecast
COMMITTED
Approved date language
Customer commitment allowed
Rule: Sales never converts “Q2 roadmap” into “available April 1.”
For strategic deals, use an explicit exception/escalation path rather than informal promises.
11
Notes: Sales needs an explicit communication contract. The exact labels here are our proposed governance, not an industry standard: Vision, Planned, Forecast and Committed. The important best-practice principle is to distinguish directional roadmap information from customer-safe delivery commitments. This gives Sales more usable information while reducing accidental promises.

## Slide 12
CTO VIEW
The CTO gets the engineering integrity view
Product Roadmap • Discovery • Delivery
Discovery maturity
Artefact Ready
Technical feasibility
Architecture decision
Dependencies
Sizing / capacity
Delivery milestones
Forecast window
Forecast confidence
Forecast movement
The CTO no longer has to use “not a roadmap” as a proxy for “not ready to promise.”
12
Notes: For the CTO, the useful view is engineering integrity: discovery maturity, readiness, dependencies, feasibility, capacity and forecast confidence. The roadmap does not remove Engineering's role in delivery commitment. It makes the transition from strategic intent to engineering commitment visible and governed.

## Slide 13
GOVERNANCE GATE
Recommended Definition of Committed
Product Roadmap • Discovery • Delivery
✓
Problem and intended outcome sufficiently validated
✓
Solution direction sufficiently validated
✓
Required PRD / product artifacts complete
✓
Prototype completed where appropriate
✓
Technical feasibility reviewed
✓
Major dependencies identified
✓
Engineering sizing completed
✓
Capacity allocated / sequencing agreed
✓
Product + Engineering explicitly approve commitment
Committed = an explicit joint decision, not a side effect of appearing in a quarter.
13
Notes: I propose that Committed be a jointly governed status. Required product artifacts are complete to the agreed threshold; feasibility and dependencies have been reviewed; scope is sufficiently understood; engineering sizing exists; and capacity has been allocated. The exact checklist can be calibrated, but the principle is that Product cannot create a delivery commitment unilaterally.

## Slide 14
OPERATING CADENCE
Run one monthly Product & Delivery Outlook
Product Roadmap • Discovery • Delivery
1
Strategy changes
Goals, customer/market evidence
2
Roadmap movement
Adds, removals, quarter changes + rationale
3
Discovery movement
Validated, Artefact Ready, paused, killed
4
Delivery forecast
Date-range / confidence / dependency changes
5
Commercial commitments
New promises, exceptions, strategic deals
6
Trade-offs
What moves if a new priority enters?
45–60 min monthly • Quarterly 90-min investment review for larger portfolio decisions
14
Notes: A monthly Product and Delivery Outlook should review movement, not re-present the entire roadmap. Which bets changed? Which discovery items matured? Which delivery forecasts narrowed or moved? Which commitments are at risk? And which trade-offs require executive decisions? This creates predictable governance without turning every roadmap review into sprint management.

## Slide 15
GOVERNANCE
Decision rights: make promises deliberately
Product Roadmap • Discovery • Delivery
Decision
Product
CTO / Eng
CEO
Sales
Goals / themes
R
C
A
C
Roadmap sequencing
R
C
A*
C
Artefact Ready
A/R
C/R
I
C
Delivery forecast
C
A/R
I
I
Committed status
R
R
A*
C
Customer date promise
C
C
A*
R†
* CEO accountability for material portfolio / strategic commitments. † Sales within approved communication policy; exceptions escalate.
15
Notes: Decision rights need to be explicit. Product owns strategic prioritization and roadmap integrity. Product and Engineering jointly govern readiness and commitment. Engineering owns credible execution forecasting with Product input. Sales owns customer conversations within the agreed communication status. Leadership arbitrates material portfolio trade-offs.

## Slide 16
ACTION PLAN
30-day implementation: fix the contract, not the tooling
Product Roadmap • Discovery • Delivery
WEEK 1
Agree definitions
Quarter • Artefact Ready • Forecast • Committed • Customer-communicable
WEEK 2
Configure views
CEO • CTO • Sales views + commitment/confidence fields
WEEK 3
Pilot
Apply to top 10–15 initiatives; resolve ambiguous dates and statuses
WEEK 4
Operate
Run first Product & Delivery Outlook; capture decisions and forecast changes
Success test: can each executive answer WHY? • HOW MATURE? • WHEN? • WHAT MAY I PROMISE? without interpreting the quarter differently?
16
Notes: This does not require a tooling migration. Week one is vocabulary and field definitions. Week two is the Definition of Committed and customer-communication rules. Week three is the CEO, CTO and Sales views in JPD. Week four is the first Product and Delivery Outlook. We fix the operating contract first and let JPD remain the source of truth.

## Slide 17
DECISION
Executive decisions requested today
Product Roadmap • Discovery • Delivery
1
Confirm JPD is the product roadmap source of truth
2
Define roadmap quarter as planning intent, not automatic delivery commitment
3
Keep Discovery Maturity + Artefact Ready as readiness model
4
Adopt a separate Forecast / Committed contract jointly with Engineering
5
Publish CEO, CTO and Sales views from the same underlying data
6
Govern customer date promises through explicit commercial status
One source of truth. Different questions. Progressively higher certainty.
17
Notes: I am asking for five decisions: agree what a roadmap quarter means; confirm Discovery Maturity and Artefact Ready as readiness signals; agree the Definition of Committed; agree the delivery-forecast confidence model; and agree what Sales may communicate at each status. Once those are explicit, most of today's disagreement should disappear.

## Slide 18
SOURCES
External best-practice anchors
Product Roadmap • Discovery • Delivery
Atlassian / JPD
JPD is a prioritization and roadmapping tool; ideas may be problems, opportunities or potential solutions; committed ideas transition to delivery.
Atlassian / Product roadmaps
Roadmaps communicate vision, direction, priorities and progress; executive roadmaps commonly use broad monthly/quarterly horizons.
Roadmaps communicate how and why ideas were prioritized; JPD supports curated views for stakeholders.
Productboard
Roadmap communicates strategic direction; release planning is the execution-level plan for delivering decided work.
Roadmap = strategic direction; release plan = execution-level delivery plan and timeframe.
Aha! + ProductPlan
Both distinguish strategic product roadmapping from more detailed release/delivery planning and recognize multiple valid roadmap formats.
Product roadmap is strategic; release roadmap focuses on timing, dependencies and launch coordination.
Product Talk + airfocus + Pendo
Discovery reduces uncertainty around outcomes, opportunities and solutions; roadmaps evolve as evidence and priorities change.
Outcomes connect to opportunities, candidate solutions and assumption testing; discovery manages uncertainty.
Audited across 25 references. Full URLs, evidence table and claim-by-claim cross-check are in the companion document.
18
Notes: The framework has now been cross-checked against a broader set of product-management and SaaS sources. The strongest direct evidence for our specific case comes from Atlassian JPD itself, which separates Discovery, Ready for delivery and Delivery. Productboard, Aha!, ProductPlan, airfocus and Pendo reinforce the broader distinction between strategic roadmapping and more detailed delivery/release planning. The companion document contains the full URLs and claim-by-claim evidence table.